EDRILL FAMILY BURSARY

Administration Procedure / SOP

Version 1.4 — Approved for controlled issue

Phase 1 • Thailand operations • Effective 1 October 2026

STATUS Final controlled procedure. This Procedure applies to each Award Year after the annual cycle authorisation has been approved.

| Document owner | Administrator | Approval authority |
| --- | --- | --- |
| Bursary Committee Chairman | Bangkok Office / Bursary Administrator | Executive Sponsor and Bursary Committee |

Document purpose

This SOP converts the approved Charter v1.3 and Eligibility and Selection Rules v1.3 into a controlled end-to-end operating process for planning, applications, screening, assessment, approval, payment, appeals, records and annual close-out.

# 1. Purpose and authority

This Procedure establishes the mandatory workflow for administering the EDrill Family Bursary. It applies to the Executive Sponsor, Bursary Committee, Bangkok Office, HR, Finance/Payroll, Operations, reviewers and any appointed labour-hire agency participating in Phase 1.

| Document layer | Operating authority |
| --- | --- |
| Charter v1.3 | Purpose, scope, funding, governance, award limits and scheme authority. |
| Eligibility and Selection Rules v1.3 | Eligibility, evidence, 100-point selection framework, ranking, appeals and exceptions. |
| This SOP v1.4 | Workflow, roles, deadlines, hand-offs, records, notifications and controls. |
| Payment and Evidence Rules v1.3 | Payment, tax, evidence, recovery and agency onward-payment controls. |
| Forms and registers | Controlled execution records; they must not alter policy or scoring rules. |
| HIERARCHY Applicable law prevails, followed by the Charter, Eligibility and Selection Rules, this SOP, Payment and Evidence Rules, and controlled forms. Any conflict must be resolved before the affected step continues. |  |

# 2. Scope and Award Year

Phase 1 applies only to Thailand operations. Each Award Year is a 12-month period approved and recorded in the applicable Annual Planning Note. Myanmar and other locations remain outside scope unless formally approved.

Business day means a normal EDPL Bangkok working day, excluding weekends and applicable Bangkok public holidays. Deadlines falling on a non-business day move to the next business day unless the published application notice expressly states otherwise.

# 3. Roles and accountabilities

| Role | Accountability |
| --- | --- |
| Executive Sponsor | Approves annual cycle authorisation and budget, final award list, material exceptions, delegations and material amendments. |
| Bursary Committee Chairman | Leads governance, confirms quorum and conflicts, chairs decisions, signs Committee recommendations and instructs controlled hand-offs. |
| Bursary Administrator / Bangkok Office | Owns timetable, controlled forms, intake, acknowledgement, completeness checks, secure records, packs, minutes, notices, appeals log and annual report. |
| HR | Verifies employment, service, salary definition, relationship/dependency and required declarations; safeguards personnel data. |
| Finance / Payroll | Confirms salary-cap eligibility, budget availability, recipient treatment, payment route, payroll/agency processing, evidence and recovery controls. |
| Operations | Confirms Thailand operational scope, rig assignment and labour-hire continuity. |
| Reviewers / Committee members | Declare conflicts, assess only allocated eligible applications, apply the approved matrix, record evidence and maintain confidentiality. |
| Labour-hire agency | Verifies employment and assignment data, follows the participation agreement, pays onward and supplies required confirmation evidence. |

No one person may complete intake, final scoring approval and payment release for the same application. Finance cannot be the sole award decision-maker, and HR may not release payment without Finance control.

# 4. Annual Administration Timetable

| Milestone | Controlled deadline | Owner |
| --- | --- | --- |
| Annual cycle authorisation approved | Before the annual announcement or application opening | Administrator / Executive Sponsor |
| Applications open | Date approved in the Annual Planning Note | Administrator |
| Applications close | Published date and cut-off time; normally after an application period of at least 30 calendar days | Administrator |
| Application acknowledged | Within 2 business days of receipt | Administrator |
| Completeness cure completed | Within 5 business days of the request, or by the published cure deadline | Administrator / Applicant |
| Eligibility screening completed | Within 10 business days after applications close or the cure period ends, whichever is later | HR / Finance / Operations |
| Reviewer scoring completed | Within 10 business days after eligibility screening is completed | Allocated reviewers |
| Committee decision meeting | Within 5 business days after reviewer scoring is completed | Chairman / Committee |
| Final award list approved | Within 3 business days after the Committee recommendation | Executive Sponsor |
| Decision notices issued | Within 2 business days after final approval | Administrator |
| Appeal lodged | Within 10 business days of the decision notice | Applicant |
| Appeal decided | Within 10 business days after receipt of a complete appeal | Independent reviewer |
| First payment | Next approved payroll or agency payment cycle after acceptance and completion of payment controls | Finance / Payroll |
| Quarterly review | Before each scheduled quarterly payment | HR / Finance |
| Award Year close | On the final day of the Award Year stated in the Annual Planning Note | Administrator / Finance |
| Annual report completed | Within 30 business days after the Award Year closes | Administrator / Committee |

# 5. Annual planning and cycle authorisation

Before each Award Year, the Administrator prepares an Annual Planning Note and an Annual Cycle Authorisation Record. The Annual Planning Note must specify:

Award Year dates, application window, decision timetable and payment quarters;

number of available award places, total budget and allocation between employee and labour-hire routes;

award limits and eligible-cost rules;

Committee membership, administrator, back-up administrator, reviewers and appeal reviewer;

current controlled-document versions and change summary;

secure submission route, storage location, access list and retention schedule;

approved applicant communications, annual reviewer briefing and scoring-calibration completion;

Finance/Payroll, tax, agency and payment readiness.

The Executive Sponsor approves the Annual Planning Note and Annual Cycle Authorisation Record before applications open. The Administrator then releases the controlled annual issue pack and archives superseded materials with clear status labels.

# 6. Application opening, submission and acknowledgement

## 6.1 Annual application communication

The Administrator issues only the approved English/Thai annual application communication. It must state the purpose, eligibility summary, award limits, number of places, Award Year, deadline and cut-off time, secure route, required evidence, Privacy Notice, appeal route and support contact. It must describe the Bursary as discretionary and must not describe it as a charity, foundation, society, public fund, donation-funded scheme, tax-free benefit or guaranteed entitlement.

## 6.2 Submission

Applicants must use the approved application form and secure submission route. Applications received elsewhere must be redirected without copying sensitive attachments into uncontrolled systems. The Administrator assigns a unique application reference and records the received timestamp.

## 6.3 Acknowledgement

Within two business days, the Administrator sends an acknowledgement containing the reference number, received date, completeness status, next step, privacy link and contact point. Receipt does not confirm eligibility or selection.

## 6.4 Late applications

A late application is not assessed unless a written exception is approved under Appeals and exceptions section. The record must state the cause, evidence, authority and why acceptance does not create unfair advantage.

# 7. Intake and completeness screening

The Administrator screens submissions without scoring them. Each application receives one controlled status:

| Status | Meaning | Required action |
| --- | --- | --- |
| Received—unreviewed | Submission logged; intake check not started. | Restrict access and begin check in sequence. |
| Incomplete—cure open | Required information or evidence is missing or unclear. | Send one consolidated request and a fixed cure deadline. |
| Complete—eligibility pending | Minimum application pack is present. | Route to HR/Finance/Operations screening. |
| Ineligible | A mandatory threshold is not met. | Record criterion and issue controlled notice after approval. |
| Exception review | A documented deviation requires authorised review. | Do not score until exception decision is recorded. |
| Eligible—scoring pending | All mandatory checks passed. | Prepare minimised Committee pack. |

Applicants must provide missing information or evidence within five business days of the Administrator’s request, or by the completeness cure deadline stated in the approved Annual Planning Note, whichever is later. The Administrator may clarify an ambiguity or explain an evidence requirement but must not coach an applicant to improve their competitive score.

# 8. Eligibility verification

HR, Finance and Operations must complete the approved Eligibility Screening Record before an application is provided to reviewers. All applicable mandatory criteria must be satisfied:

- The applicant is an eligible EDrill employee or an eligible employee of an approved labour-hire agency assigned to EDrill rigs in Thailand.

- The applicant has completed at least 21 months of continuous eligible service or assignment immediately before the first day of the relevant Award Year, with no single break exceeding 30 days, unless a written exception has been approved.

- The applicant’s gross fixed monthly salary is below THB 100,000 on the approved eligibility assessment date for the relevant Award Year. Variable pay, overtime, bonuses, allowances, reimbursements and one-off payments are excluded.

- The child is 12 years of age or younger throughout the relevant Award Year.

- The applicant’s relationship to, or legal dependency for, the child has been verified.

- The child is enrolled in a recognised school in Thailand.

- All required evidence is complete and authentic, including any required translation or independent verification.

- The applicant has declared any other education assistance received for the child, and no prohibited duplicate funding applies to the same eligible cost.

Salary, employment, service and assignment information should be verified internally wherever practicable. Applicants should not be required to submit payslips unless Finance approves a documented exception. Raw salary records and unnecessary child or family documents must not be included in Committee review packs.

FALSE INFORMATION Suspected false, misleading or withheld material information is referred to HR and the Chairman. Assessment or payment is paused until the issue is resolved and recorded.

# 9. Labour-hire participation gate

Labour-hire applications are accepted only when the appointed agency participation agreement is signed and the cycle is enabled in the annual planning note. The Administrator keeps labour-hire records separately identified for payment and reporting controls.

Agency verifies employment status and the applicant’s identity.

Operations verifies the applicant’s assignment to EDrill rigs and confirms that the applicant has completed at least 21 months of continuous eligible service or assignment immediately before the first day of the relevant Award Year, with no single break exceeding 30 days, unless a written exception has been approved.

Agency and EDPL roles for privacy, verification, tax/payment, onward payment, records and audit evidence are recorded.

Labour-hire communications do not describe the applicant as an EDrill employee.

EDPL pays the agency only after final award approval and recipient acceptance, and before the relevant scheduled quarterly payment.

Agency supplies onward-payment acknowledgement and retains employee receipt evidence as required.

GATE FAILURE If the agency agreement or any mandatory control is incomplete, labour-hire participation is unavailable for that Award Year. Employee applications may proceed if their applicable annual cycle and eligibility controls are complete.

# 10. Committee pack and reviewer allocation

The Administrator prepares a minimised pack only for eligible applications. Each pack contains the application reference, eligibility result, approved salary/need band, dependant/family indicators, evidenced eligible school costs, service/continuity band, evidence checklist result and any approved exception. It excludes raw salary records, bank details and unnecessary identity documents.

Before access is granted, every reviewer signs current confidentiality and conflict declarations. The Chairman allocates at least two non-conflicted reviewers per application where practicable. A conflicted person must not access, score, deliberate, vote on or hear an appeal for that application.

# 11. Scoring, moderation and ranking

Reviewers use the controlled Review Sheet v1.3 and its approved banded matrix. No reviewer may create personal weighting, use academic merit, reward unsupported assertions or consider prior award status.

| Category | Maximum | Procedure control |
| --- | --- | --- |
| Financial need and salary | 35 | Apply the approved salary/need band supported by HR/Finance-verified data. |
| Family circumstances and dependants | 25 | Apply only defined evidence-based family and hardship bands. |
| School cost burden | 15 | Use evidenced eligible compulsory costs under the approved cost method. |
| Service / continuity | 15 | Use verified service or assignment band. |
| Evidence completeness | 10 | Use the published checklist; irrelevant documents receive no credit. |
| Prior award status | 0 | No renewal priority or preference. |

Each reviewer records points and a concise evidence reference for every category. The Administrator compares reviewer totals. A material difference, defined in the Review Sheet, requires documented moderation before the Committee meeting; reviewers must not simply average unexplained scores.

Eligible applications are ranked by descending total. Ties are resolved in order: higher Financial need and salary score; higher Family circumstances and dependants score; higher School cost burden score; earlier timestamp of a complete application; then a supervised random draw with two witnesses. The Chair has no discretionary tie-break outside this sequence.

CALIBRATION Before live scoring, reviewers must complete the same three approved calibration cases and the Administrator must record that the results are acceptably aligned. A missing or mismatched matrix blocks scoring.

# 12. Committee decision and final approval

The Phase 1 Committee operates under its approved Terms of Reference. Quorum is three non-conflicted members, including the Chairman or written delegate and at least one Finance or HR representative. Decisions are by majority; the Chairman has a casting vote only when not conflicted.

The Administrator records attendance, quorum, conflicts, recusals, application reference, reviewer scores, moderation, ranking, available places, recommended amount, conditions, reasons, vote and dissent. The maximum is six award places, subject to approved budget. Each child is assessed separately; multiple children from one family may be selected, but each child may receive only one award for the Award Year.

The Committee recommends the award list. The Executive Sponsor approves the final award list and material exceptions. No notice or payment instruction is issued until that approval is recorded.

# 13. Notifications and acceptance

## 13.1 Successful applicant

The Administrator issues the approved award letter within two business days of final approval. It states the child/reference, Award Year, approved amount, eligible costs, quarterly schedule, payment route, evidence conditions, change-notification duty, privacy reference, false-information consequences, recovery rights, no automatic renewal and appeal/contact route. Payment cannot begin until the recipient accepts the conditions in writing.

## 13.2 Unsuccessful or ineligible applicant

The notice states the outcome, whether it arose from eligibility or limited places, the permitted appeal grounds, secure appeal route and 10-business-day deadline. It must not disclose another applicant’s information, comparative ranking or confidential Committee deliberations.

# 14. Payment instruction and release

The Chairman authorises the controlled hand-off after final approval and acceptance. Finance/Payroll independently confirms the payment gate:

approved award list and amount;

accepted award conditions;

continued eligibility and complete required evidence;

approved payment route and recipient-treatment record;

budget, cost centre/GL, tax, withholding, reporting and payslip treatment;

privacy/consent controls and no unresolved compliance issue;

agency agreement and verified payment details for labour-hire recipients.

| Recipient route | Maximum | Release method |
| --- | --- | --- |
| EDrill employee child | Up to THB 120,000 per Award Year | Quarterly through normal payroll into the employee bank account and shown as a payslip line item. |
| Labour-hire employee child | Up to THB 8,000 per month; THB 96,000 per Award Year | Quarterly in arrears to the appointed agency after approval/acceptance and before onward payment. |

Direct school payment, reimbursement, cash or advance payment is prohibited unless Finance and the Executive Sponsor approve a written exception with evidence, recipient treatment and recovery controls. Payment must not exceed the approved amount or evidenced eligible costs.

# 15. Quarterly review, changes and recovery

Before each quarterly payment, HR and Finance complete a Quarterly Payment Review confirming employment/assignment, school enrolment, evidence for eligible costs, prior-payment evidence, duplicate funding, unresolved compliance matters and amount due. The agency must reconfirm status where required by its agreement.

Recipients must promptly report changes to employment, assignment, salary, schooling, age, dependency, school cost, duplicate support or submitted information. The Committee may continue, suspend, cease or prorate the award from a documented effective date. Finance, HR and the recipient/agency coordinate any recovery. The decision record states evidence, authority, amount, notice, repayment/offset route and any legal or hardship considerations.

# 16. Appeals and exceptions

## 16.1 Appeals

An applicant may appeal within 10 business days of the decision notice using the approved form and secure route. Grounds are limited to procedural error, new material evidence, exceptional hardship or incorrect eligibility assessment. The Administrator acknowledges the appeal within two business days and checks completeness without determining the merits.

An independent reviewer decides within 10 business days after a complete appeal, subject to a recorded reasonable extension for verification. If the Chair participated in the original decision or is conflicted, the Executive Sponsor appoints an alternative reviewer. The appeal record includes ground, evidence, original record, conflicts, findings, decision, reasons and any consequential action. An appeal cannot create eligibility or additional award places.

## 16.2 Exceptions

An exception must be written, evidence-based, time-limited and approved by the designated authority before it affects assessment or payment. It must not bypass the six-place limit without Executive Sponsor authority, create a hidden scoring advantage, waive privacy/child-data controls or contradict applicable law. The Administrator records the rule, reason, evidence, authority, duration and affected applications.

# 17. Privacy, security and records

The Administrator operates the scheme under the approved Privacy Notice, consent wording where required, data map, access roles and retention schedule. Only information necessary for eligibility, selection, payment, appeals, audit and legal compliance may be collected or retained.

Store Bursary records in a dedicated EDrill-managed SharePoint site or document library protected by role-based access controls.

Restrict full applications, identity documents, salary information, consents and payment records to personnel who require them for their assigned duties. Committee members receive only anonymised or minimised assessment packs unless additional access is specifically required and authorised.

Use named EDrill accounts and approved security groups. Anonymous or “Anyone” links and external sharing from the Bursary SharePoint location are prohibited. Any necessary agency exchange must use the separately approved secure transfer route.

Review access before each Award Year and remove access promptly when a person’s assigned duties end. Apply approved sensitivity, download and retention controls where technically available.

Transmit applicant information only through approved secure channels and do not circulate applicant packs through general email distribution lists.

Record authorised recipients and any cross-border access or transfer in accordance with the Privacy Notice and approved data-transfer controls.

Retain and securely delete records according to the approved retention schedule. Suspend deletion when a documented legal hold, investigation or audit applies.

Do not publish beneficiary names, photographs or personal stories without specific written consent.

Record and promptly escalate any suspected privacy or information-security incident under applicable EDrill procedures.

# 18. Communications control

All applicant-facing messages use approved templates and the same terms, thresholds, dates and version references as the controlled documents. The Administrator performs a pre-release check for accuracy, translation consistency, recipients, attachments, privacy exposure and approval. Communications must not promise an award, claim tax-free treatment, solicit donations or describe the scheme as a charity, foundation, society or public fund.

# 19. Award Year close and annual review

Within 30 business days after the Award Year ends, the Administrator and Finance reconcile awards, scheduled and actual payments, unpaid amounts, evidence, changes, recoveries, appeals, exceptions and retained records. The Administrator prepares an anonymised annual report covering applications, eligibility, awards, total approved and paid value, employee/labour-hire split, multiple-child awards, appeals, exceptions, control failures, privacy incidents, recovery activity and recommendations.

The Committee reviews the report and recommends continuation or change. The Executive Sponsor approves the next-cycle decision, budget and any material amendments. No prior recipient receives renewal priority; every new Award Year begins with a fresh eligibility and selection assessment.

# 20. Deviations, amendments and document control

Operational deviations are recorded in the Decision Log and resolved by the authority assigned in the Charter and Terms of Reference. A material amendment to eligibility, award values, places, scoring, privacy, payment route, agency participation, appeals or governance requires approval and coordinated version updates across all affected documents before use.

The Administrator maintains a controlled document register showing title, owner, version, approval date, effective date, status, location and superseded version. Printed or downloaded copies are uncontrolled unless specifically stamped and recorded.

# Appendix A — End-to-end control matrix

| Stage | Entry condition | Output / evidence | Control owner |
| --- | --- | --- | --- |
| 1. Plan | Prior Award Year closed and annual cycle authorisation confirmed | Annual Planning Note; approved budget; timetable; Annual Cycle Authorisation Record | Administrator / Sponsor |
| 2. Open | Annual cycle authorisation approved | Approved annual communication and application pack released | Administrator |
| 3. Receive | Secure route active | Reference, timestamp and acknowledgement | Administrator |
| 4. Complete | Application logged | Completeness status and cure record | Administrator |
| 5. Verify | Complete application | Eligibility Screening Record | HR / Finance / Operations |
| 6. Prepare | Eligible application | Minimised pack; reviewer allocation; declarations | Administrator / Chair |
| 7. Score | Approved matrix and calibration complete | Two reviewer sheets; moderation record; ranking | Reviewers / Administrator |
| 8. Decide | Quorum and conflicts confirmed | Committee minute and recommended list | Committee |
| 9. Approve | Budget and decision record complete | Executive Sponsor final award approval | Executive Sponsor |
| 10. Notify | Final approval recorded | Outcome notice; acceptance or appeal clock | Administrator |
| 11. Pay | Acceptance and payment gates complete | Payroll/agency instruction and payment record | Finance / Payroll |
| 12. Monitor | Quarterly payment due | Quarterly Review; change/recovery decision | HR / Finance / Committee |
| 13. Appeal | Complete appeal received on time | Independent appeal decision and notice | Independent reviewer |
| 14. Close | Award Year ended | Reconciliation, annual report and next-cycle decision | Administrator / Committee / Sponsor |

# Appendix B — Mandatory controlled records

| Record | Minimum content | Owner |
| --- | --- | --- |
| Annual Planning Note | Award Year, timetable, places, budget, document versions, roles, payment arrangements and communications | Administrator |
| Annual Cycle Authorisation Record | Cycle approval, evidence references, authoriser and approval date | Administrator |
| Application Register | Reference, received time, status and applicant communications | Administrator |
| Eligibility Screening Record | Each mandatory criterion, verifier, evidence and result | HR / Finance / Operations |
| Conflict and Confidentiality Register | Declaration, relationship, recusal, access restriction and date | Chairman / Administrator |
| Review Sheet and Moderation Record | Category points, evidence references, reviewer, variance and resolution | Reviewers / Administrator |
| Committee Decision Record | Quorum, conflicts, scores, ranking, decision, vote, reasons and conditions | Administrator / Chairman |
| Final Award Approval | Approved list, amount, route, conditions and Sponsor approval | Executive Sponsor |
| Payment and Quarterly Review Record | Eligibility, evidence, amount, route, treatment, release and onward-payment evidence | Finance / Payroll |
| Appeal and Exception Register | Ground, evidence, conflicts, authority, decision, reasons and date | Administrator |
| Change / Recovery Record | Effective date, evidence, amount, decision, notice and recovery route | HR / Finance / Committee |
| Annual Report | Volumes, values, outcomes, controls, issues and recommendations | Administrator / Committee |

# Revision history

| Version | Date | Status | Summary |
| --- | --- | --- | --- |
| 0.1 | June 2026 | Draft for internal review | Initial procedure covering planning through annual review. |
| 1.3 | 26 August 2026 | Approved for controlled issue | Aligned with Charter and Eligibility Rules v1.3; corrected scoring, agency timing, governance, appeals, privacy and records controls. |
| 1.4 | 26 August 2026 | Approved for controlled issue | Converted the SOP to a perpetual annual procedure; removed first-launch controls and fixed Award Year, labour-hire, SharePoint/privacy, appendix and version-control defects. |

## Controlled approval record

Approval of this SOP is evidenced by the signed Final Issue Approval Record. Operation for each Award Year is authorised separately through the approved Annual Cycle Authorisation Record. The sign-off points for this controlled SOP issue are:

| Approval role | Decision / signature | Date |
| --- | --- | --- |
| Executive Sponsor | Approved for controlled issue: ______________________________ | ________________ |
| Bursary Committee Chairman | Approved for controlled issue: ______________________________ | ________________ |
| HR / Bangkok Administrator | Procedure and records controls confirmed: __________________ | ________________ |
| Finance / Payroll | Payment and recipient-treatment controls confirmed: _________ | ________________ |
| Operations | Assignment verification controls confirmed: ________________ | ________________ |

## Related controlled documents

| Document | Required relationship |
| --- | --- |
| Charter v1.3 | Higher-level authority for scope, governance, awards and annual operation. |
| Eligibility and Selection Rules v1.3 | Same eligibility thresholds, 100-point categories, ranking and appeals. |
| Payment and Evidence Rules v1.3 | Implements payment, tax, evidence, recovery and agency controls. |
| Committee Terms of Reference v1.0 | Implements quorum, voting, recusal, confidentiality and delegation. |
| Review Sheet v1.3 | Carries approved bands, tie-breaks, evidence references and moderation control. |
| Privacy Notice / Records Schedule v1.0 | Implements lawful processing, rights, access, retention and deletion. |
| Application and communication pack v1.3 | Implements approved fields, notices, deadlines and applicant communications. |